## Instructions
Step | Instruction | Evidence location
1 | Open the Scrum activity tool and review the framework view. | Evidence row 1
2 | Separate predictable work from complex work in the evidence sheet. | Evidence row 2
3 | Map current feedback delays and waste points. | Evidence row 3
4 | Apply Agile values, empiricism, and Scrum values to propose a two-Sprint experiment. | Evidence row 4
5 | Define evidence that would support continue, adapt, or stop. | Evidence row 5
6 | Present the diagnostic and receive peer challenge. | Evidence row 6

## Evidence
ID | Question or checkpoint | Evidence / decision | Accountable owner | Measure / review trigger | Status
1 | Where does uncertainty invalidate the existing plan? |  |  |  | Not started
2 | Which feedback loop should be shortened first? |  |  |  | Not started
3 | How do transparency, inspection, and adaptation operate in the proposal? |  |  |  | Not started
4 | What waste or defect signal should improve? |  |  |  | Not started
5 | Define evidence that would support continue, adapt, or stop. |  |  |  | Not started
6 | Present the diagnostic and receive peer challenge. |  |  |  | Not started

## Scenario Data
Item | Signal | Baseline | Target | Owner | Status
S01 | Customer feedback cadence | Monthly | Every Sprint | Product Owner | Open
S02 | Cycle time (days) | 9 | 6 | Developers | Open
S03 | Escaped defects | 12 | 6 | Developers | Open
S04 | Owned improvement actions | 0 | 1 | Scrum Team | Open
S05 | Stakeholder evidence reviewed | 1 | 4 | Product Owner | Open

## Summary
Measure | Value
Evidence rows | 6
Completed rows | 0
Completion rate | 0%