## Instructions
Step | Instruction | Evidence location
1 | Record the impediment in the Scrum tool and distinguish symptom from system cause. | Evidence row 1
2 | Interview each role using open coaching questions. | Evidence row 2
3 | Map what the team can solve, what needs facilitation, and what needs organisational escalation. | Evidence row 3
4 | Facilitate a joint experiment with an owner and timebox. | Evidence row 4
5 | Define lead-time and quality evidence. | Evidence row 5
6 | Debrief whether the Scrum Master enabled ownership or became the owner. | Evidence row 6

## Evidence
ID | Question or checkpoint | Evidence / decision | Accountable owner | Measure / review trigger | Status
1 | What makes this an impediment rather than ordinary work? |  |  |  | Not started
2 | Who is closest to each decision? |  |  |  | Not started
3 | What systemic condition sustains the delay? |  |  |  | Not started
4 | How will the team know the experiment worked? |  |  |  | Not started
5 | Define lead-time and quality evidence. |  |  |  | Not started
6 | Debrief whether the Scrum Master enabled ownership or became the owner. |  |  |  | Not started

## Scenario Data
Item | Signal | Baseline | Target | Owner | Status
S01 | Customer feedback cadence | Monthly | Every Sprint | Product Owner | Open
S02 | Cycle time (days) | 9 | 6 | Developers | Open
S03 | Escaped defects | 12 | 6 | Developers | Open
S04 | Owned improvement actions | 0 | 1 | Scrum Team | Open
S05 | Stakeholder evidence reviewed | 1 | 4 | Product Owner | Open

## Summary
Measure | Value
Evidence rows | 6
Completed rows | 0
Completion rate | 0%