## Instructions
Step | Instruction | Evidence location
1 | Load the supplied Product Backlog worksheet and review the Scrum tool planning view. | Evidence row 1
2 | Clarify Product Goal, capacity, Definition of Done, and dependencies. | Evidence row 2
3 | Facilitate why, what, and how without assigning tasks. | Evidence row 3
4 | Draft and test one outcome-oriented Sprint Goal. | Evidence row 4
5 | Build a Sprint Backlog forecast and identify the first adaptation trigger. | Evidence row 5
6 | Run a confidence check and capture unresolved risk. | Evidence row 6

## Evidence
ID | Question or checkpoint | Evidence / decision | Accountable owner | Measure / review trigger | Status
1 | Why is the Sprint valuable? |  |  |  | Not started
2 | What evidence supports the forecast? |  |  |  | Not started
3 | How does the Sprint Goal allow flexible scope? |  |  |  | Not started
4 | Which dependency needs an explicit plan? |  |  |  | Not started
5 | Build a Sprint Backlog forecast and identify the first adaptation trigger. |  |  |  | Not started
6 | Run a confidence check and capture unresolved risk. |  |  |  | Not started

## Scenario Data
Item | Signal | Baseline | Target | Owner | Status
S01 | Customer feedback cadence | Monthly | Every Sprint | Product Owner | Open
S02 | Cycle time (days) | 9 | 6 | Developers | Open
S03 | Escaped defects | 12 | 6 | Developers | Open
S04 | Owned improvement actions | 0 | 1 | Scrum Team | Open
S05 | Stakeholder evidence reviewed | 1 | 4 | Product Owner | Open

## Summary
Measure | Value
Evidence rows | 6
Completed rows | 0
Completion rate | 0%