## Instructions
Step | Instruction | Evidence location
1 | Use the Scrum tool board and mock flow data to inspect progress toward the Sprint Goal. | Evidence row 1
2 | Identify work-in-progress, aging items, blockers, and dependency signals. | Evidence row 2
3 | Design a 15-minute Developer-owned structure. | Evidence row 3
4 | Run the event with the facilitator silent for the first five minutes. | Evidence row 4
5 | Move detailed problem-solving to a follow-up huddle. | Evidence row 5
6 | Compare baseline and redesigned behaviours. | Evidence row 6

## Evidence
ID | Question or checkpoint | Evidence / decision | Accountable owner | Measure / review trigger | Status
1 | What decision must the Daily Scrum enable? |  |  |  | Not started
2 | Which items threaten the Sprint Goal? |  |  |  | Not started
3 | What should happen after the 15 minutes? |  |  |  | Not started
4 | How can the Scrum Master coach without taking over? |  |  |  | Not started
5 | Move detailed problem-solving to a follow-up huddle. |  |  |  | Not started
6 | Compare baseline and redesigned behaviours. |  |  |  | Not started

## Scenario Data
Item | Signal | Baseline | Target | Owner | Status
S01 | Customer feedback cadence | Monthly | Every Sprint | Product Owner | Open
S02 | Cycle time (days) | 9 | 6 | Developers | Open
S03 | Escaped defects | 12 | 6 | Developers | Open
S04 | Owned improvement actions | 0 | 1 | Scrum Team | Open
S05 | Stakeholder evidence reviewed | 1 | 4 | Product Owner | Open

## Summary
Measure | Value
Evidence rows | 6
Completed rows | 0
Completion rate | 0%