## Instructions
Step | Instruction | Evidence location
1 | Load the metrics workbook and view the built-in editable charts. | Evidence row 1
2 | Compare burndown, burnup, throughput, cycle time, and aging work. | Evidence row 2
3 | Separate observation from interpretation and judgement. | Evidence row 3
4 | Identify scope, flow, quality, and dependency hypotheses. | Evidence row 4
5 | Choose one improvement experiment and leading indicator. | Evidence row 5
6 | Explain why velocity should not rank teams. | Evidence row 6

## Evidence
ID | Question or checkpoint | Evidence / decision | Accountable owner | Measure / review trigger | Status
1 | What does each chart reveal and conceal? |  |  |  | Not started
2 | Which change is scope rather than delivery? |  |  |  | Not started
3 | What additional evidence is needed before acting? |  |  |  | Not started
4 | Which metric supports the Sprint Goal decision? |  |  |  | Not started
5 | Choose one improvement experiment and leading indicator. |  |  |  | Not started
6 | Explain why velocity should not rank teams. |  |  |  | Not started

## Scenario Data
Item | Signal | Baseline | Target | Owner | Status
S01 | Customer feedback cadence | Monthly | Every Sprint | Product Owner | Open
S02 | Cycle time (days) | 9 | 6 | Developers | Open
S03 | Escaped defects | 12 | 6 | Developers | Open
S04 | Owned improvement actions | 0 | 1 | Scrum Team | Open
S05 | Stakeholder evidence reviewed | 1 | 4 | Product Owner | Open

## Summary
Measure | Value
Evidence rows | 6
Completed rows | 0
Completion rate | 0%

## Metrics
Day | Ideal remaining | Actual remaining | Scope | Done
1 | 40 | 40 | 40 | 0
2 | 36 | 39 | 40 | 3
3 | 32 | 37 | 40 | 6
4 | 28 | 35 | 44 | 10
5 | 24 | 31 | 44 | 14
6 | 20 | 28 | 44 | 19
7 | 16 | 25 | 48 | 25
8 | 12 | 18 | 48 | 31
9 | 8 | 12 | 48 | 36
10 | 4 | 6 | 48 | 42