## Instructions
Step | Instruction | Evidence location
1 | Open the Scrum tool backlog view and supplied Product Backlog workbook. | Evidence row 1
2 | Clarify Product Goal and customer/business evidence. | Evidence row 2
3 | Score items for value, risk reduction, learning, size, and dependency. | Evidence row 3
4 | Use MoSCoW or weighted ordering as a conversation aid, not an automatic answer. | Evidence row 4
5 | Refine the top items with Developers and record assumptions. | Evidence row 5
6 | Publish the ordered backlog and rationale. | Evidence row 6

## Evidence
ID | Question or checkpoint | Evidence / decision | Accountable owner | Measure / review trigger | Status
1 | Which evidence supports value? |  |  |  | Not started
2 | What risk or learning should move earlier? |  |  |  | Not started
3 | Which dependency changes the order? |  |  |  | Not started
4 | Where must Product Owner judgement override a score? |  |  |  | Not started
5 | Refine the top items with Developers and record assumptions. |  |  |  | Not started
6 | Publish the ordered backlog and rationale. |  |  |  | Not started

## Scenario Data
Item | Signal | Baseline | Target | Owner | Status
S01 | Customer feedback cadence | Monthly | Every Sprint | Product Owner | Open
S02 | Cycle time (days) | 9 | 6 | Developers | Open
S03 | Escaped defects | 12 | 6 | Developers | Open
S04 | Owned improvement actions | 0 | 1 | Scrum Team | Open
S05 | Stakeholder evidence reviewed | 1 | 4 | Product Owner | Open

## Summary
Measure | Value
Evidence rows | 6
Completed rows | 0
Completion rate | 0%