Tertiary Infotech Academy Pte Ltd

UEN: 201200696W

LEARNER GUIDE

For

Scrum Master Fundamentals for High-Performing Teams

TGS Ref No: TGS-2024045803

Conducted by

Tertiary Infotech Academy Pte Ltd

UEN: 201200696W

Version 6.0

DOCUMENT VERSION CONTROL RECORD

| Version Number | Effective Date of Release | Summary of Included Changes | Author |
| --- | --- | --- | --- |
| 1.0 | 21 May 2024 | Initial Learner Guide release. | Tertiary Infotech Academy Pte Ltd |
| 2.0 | 17 October 2025 | Updated organisation name and course alignment. | Tertiary Infotech Academy Pte Ltd |
| 6.0 | 22 August 2026 | Rebuilt from the legacy deck and current sources with five aligned topics, ten detailed activities, Scrum tool guidance, evidence, and acceptance criteria. | Dr. Alfred Ang |

TABLE OF CONTENTS

Right-click and choose “Update Field”, or press F9, to build the table of contents.

# How to Use This Guide

The PowerPoint explains concepts and decisions visually. This Learner Guide contains the detailed step-by-step procedures, realistic scenarios, tool instructions, questions, evidence requirements, and acceptance criteria intentionally kept out of the slides.

# Learning Outcomes

LO1: Implement Agile Scrum practices to analyze business requirements.

LO2: Manage Scrum role responsibilities in accordance with organizational policies.

LO3: Measure and experiment with Scrum meetings and change management methodologies.

LO4: Organize and assess work with Scrum project management in alignment with Agile values.

LO5: Share information on Agile artifacts within and across teams to foster collaboration.

# Using the Scrum Activity Tool

Open https://alfredang.github.io/scrum/ in a modern browser. The tool supports the course activities; it does not replace the Scrum Team's judgement or the official Scrum Guide.

## Before an activity

1. Open the individual Activity-XX folder and read README.pdf.

2. Open SCENARIO.pdf and mark facts, assumptions, goals, and constraints.

3. Open worksheet.xlsx and keep the Instructions sheet visible.

4. Open the Scrum activity tool in a second browser tab.

## During an activity

1. Select the matching framework, accountability, event, artifact, or metric view.

2. Enter only the scenario data supplied in the activity folder.

3. Record decisions and rationale in worksheet.xlsx, not only in the browser.

4. Use the tool output as evidence to inspect; do not treat a score as an automatic decision.

## After an activity

1. Complete every evidence sheet in worksheet.xlsx.

2. Check the expected result against CHECKLIST.pdf.

3. Save the workbook with your team name and activity number.

4. Submit the evidence requested by the trainer and retain a copy for the debrief.

# Topic 1 - Scrum Foundations

Alignment: K1, K2, K6, K7, A3. Agile mindset | empiricism | values | framework | complexity.

## Why Agile Exists

Scrum Master pitch: Agility is the ability to change direction without losing purpose.

Complex work defeats long-range certainty

Early value creates evidence

Customer feedback changes priorities

Teams learn through short cycles

Workplace signal: a plan defended after evidence changes. Better move: Shorten the feedback loop and re-plan from what is known.

## Agile Values as Decision Tests

Scrum Master pitch: The values guide trade-offs; they do not ban process, documentation, contracts, or plans.

Individuals and interactions

Working outcomes

Customer collaboration

Responding to change

Workplace signal: a process followed despite a worse outcome. Better move: Ask which choice improves learning and customer value now.

## Scrum Is a Lightweight Framework

Scrum Master pitch: Scrum provides the minimum structure needed to expose reality and improve.

One Scrum Team

Three accountabilities

Five events

Three artifacts and commitments

Workplace signal: extra roles quietly taking accountability. Better move: Return ownership to the Scrum Team and make work transparent.

## Empiricism: Transparency-Inspection-Adaptation

Scrum Master pitch: Inspection without adaptation is reporting theatre.

Transparency creates a shared view

Inspection compares reality with intent

Adaptation changes product or process

Cadence makes learning routine

Workplace signal: metrics reviewed with no decision. Better move: Name the decision each inspection can trigger.

## Scrum Values Create the Climate

Scrum Master pitch: Values are observable behaviours, not posters on a wall.

Commitment to goals

Focus on the Sprint

Openness about work

Respect for capable people

Courage to address problems

Workplace signal: a blocker hidden to protect appearances. Better move: Reward early truth and responsible experimentation.

## Activity 01 - Diagnose Scrum Foundations at HarborHealth

Alignment: K1, K2, K6, K7, A3

### Scenario

HarborHealth is replacing a patient-booking service. Leaders approved a twelve-month requirements plan, but regulations, clinic workflows, and patient expectations are changing monthly. Teams report defects late and customer feedback arrives only at final acceptance.

### Roles

Scrum Master

Product Owner

Developer

Clinic stakeholder

Observer

### Files and tool

Open activities/Activity-01-*/README.pdf for the full brief.

Open worksheet.xlsx and work from the Instructions sheet.

Open SCENARIO.pdf and CHECKLIST.pdf beside the workbook.

Use the Scrum activity tool where instructed: https://alfredang.github.io/scrum/

### Detailed playbook

1. Open the Scrum activity tool and review the framework view.

2. Separate predictable work from complex work in the evidence sheet.

3. Map current feedback delays and waste points.

4. Apply Agile values, empiricism, and Scrum values to propose a two-Sprint experiment.

5. Define evidence that would support continue, adapt, or stop.

6. Present the diagnostic and receive peer challenge.

### Facilitator and learner questions

1. Where does uncertainty invalidate the existing plan?

2. Which feedback loop should be shortened first?

3. How do transparency, inspection, and adaptation operate in the proposal?

4. What waste or defect signal should improve?

### Evidence to submit

Complexity and landscape diagnostic

Feedback-loop map

Two-Sprint experiment canvas

### Acceptance criteria

Uses current and future business/customer evidence

Explains all three pillars of empiricism

Links Agile values to decisions

Defines a measurable experiment

Save the completed workbook as Activity-01-<TeamName>.xlsx. Complete every checkpoint in CHECKLIST.pdf before submitting the evidence pack.

# Topic 2 - Scrum Accountabilities and High-Performing Teams

Alignment: K3, K5, A7. Scrum Master | Product Owner | Developers | self-management | team norms.

## One Team, Three Accountabilities

Scrum Master pitch: Accountability clarifies ownership without creating silos.

Product Owner maximizes value

Scrum Master improves effectiveness

Developers create the Increment

All share one Product Goal

Workplace signal: work bouncing between role boundaries. Better move: Use the shared goal to reconnect decisions.

## The Scrum Master Is Accountable for Effectiveness

Scrum Master pitch: A Scrum Master creates conditions for the team to solve, learn, and improve.

Establish Scrum as defined

Coach self-management

Remove impediments

Enable useful events

Serve team, Product Owner, and organization

Workplace signal: the Scrum Master acting as meeting secretary. Better move: Coach the system instead of owning the team's work.

## Product Owner: Value and Product Backlog

Scrum Master pitch: The Product Owner may delegate work but remains accountable for value decisions.

Develop and communicate Product Goal

Create clear Product Backlog items

Order work

Ensure transparency and understanding

Workplace signal: a committee with no final value decision. Better move: Make one accountable Product Owner visible.

## Developers: A Usable Increment Every Sprint

Scrum Master pitch: Self-management means owning how work is turned into value.

Create the Sprint plan

Build quality through Definition of Done

Adapt daily toward Sprint Goal

Hold one another professionally accountable

Workplace signal: tasks assigned by an external manager. Better move: Let Developers plan and adapt the work.

## Build a High-Performing Team System

Scrum Master pitch: Performance grows when candour and accountability reinforce each other.

Cross-functional skills

Psychological safety

Working agreements

Stable membership

Visible dependencies

Workplace signal: polite silence masking risk. Better move: Create explicit norms for dissent, decisions, and help.

## Activity 02 - Create Accountabilities and Working Agreements

Alignment: K3, K5, A7

### Scenario

A digital payments team has a Product Owner, Scrum Master, developers, architects, and line managers, but decisions are slow. Managers assign Sprint tasks, the Scrum Master writes status reports, and the Product Owner shares backlog control with a steering committee.

### Roles

Scrum Master

Product Owner

Developer

Line manager

Governance representative

### Files and tool

Open activities/Activity-02-*/README.pdf for the full brief.

Open worksheet.xlsx and work from the Instructions sheet.

Open SCENARIO.pdf and CHECKLIST.pdf beside the workbook.

Use the Scrum activity tool where instructed: https://alfredang.github.io/scrum/

### Detailed playbook

1. Use the Scrum tool accountabilities view to identify ownership gaps.

2. Map current decisions against Scrum accountabilities and organisational policy.

3. Identify conflicts, delegations, and escalation points.

4. Draft six working agreements for decisions, dissent, focus, help, quality, and handoffs.

5. Run a role-boundary negotiation using the scenario cards.

6. Record owners and review triggers.

### Facilitator and learner questions

1. Which accountability is currently diluted?

2. What can be delegated without transferring accountability?

3. How will policies be respected without removing self-management?

4. Which norm makes disagreement safe and useful?

### Evidence to submit

Accountability decision map

Working agreement canvas

Ownership and escalation matrix

### Acceptance criteria

Covers Product Owner, Scrum Master, and Developers

Separates accountability from job title

Aligns with organisational policy

Makes decision and escalation rules observable

Save the completed workbook as Activity-02-<TeamName>.xlsx. Complete every checkpoint in CHECKLIST.pdf before submitting the evidence pack.

## Activity 03 - Coach a Team Through an Impediment

Alignment: K3, K5, A7

### Scenario

A retail platform team loses two days each Sprint waiting for a security review. Developers want the Scrum Master to chase approvals; Security says requests arrive incomplete; the Product Owner keeps adding urgent compliance items mid-Sprint.

### Roles

Scrum Master coach

Developer

Product Owner

Security partner

Observer

### Files and tool

Open activities/Activity-03-*/README.pdf for the full brief.

Open worksheet.xlsx and work from the Instructions sheet.

Open SCENARIO.pdf and CHECKLIST.pdf beside the workbook.

Use the Scrum activity tool where instructed: https://alfredang.github.io/scrum/

### Detailed playbook

1. Record the impediment in the Scrum tool and distinguish symptom from system cause.

2. Interview each role using open coaching questions.

3. Map what the team can solve, what needs facilitation, and what needs organisational escalation.

4. Facilitate a joint experiment with an owner and timebox.

5. Define lead-time and quality evidence.

6. Debrief whether the Scrum Master enabled ownership or became the owner.

### Facilitator and learner questions

1. What makes this an impediment rather than ordinary work?

2. Who is closest to each decision?

3. What systemic condition sustains the delay?

4. How will the team know the experiment worked?

### Evidence to submit

Impediment cause map

Coaching record

Escalation and experiment plan

### Acceptance criteria

Separates symptom and cause

Preserves team ownership

Includes organisational service where needed

Uses evidence and a review date

Save the completed workbook as Activity-03-<TeamName>.xlsx. Complete every checkpoint in CHECKLIST.pdf before submitting the evidence pack.

# Topic 3 - Scrum Events and Facilitation

Alignment: K4, A4, A5. Sprint | Planning | Daily Scrum | Review | Retrospective | refinement.

## The Sprint Is the Container

Scrum Master pitch: Every Sprint turns an idea into a usable learning opportunity.

Fixed length of one month or less

Product Goal remains the compass

Quality does not decrease

Scope may be clarified with Product Owner

Workplace signal: scope churn erasing the Sprint Goal. Better move: Negotiate scope while protecting the goal and quality.

## Sprint Planning Answers Three Questions

Scrum Master pitch: A strong Sprint Goal gives coherence to flexible scope.

Why is this Sprint valuable?

What can be Done?

How will the work get Done?

Capacity, quality, and dependencies inform the plan

Workplace signal: a backlog shopping list without purpose. Better move: Write one outcome-oriented Sprint Goal first.

## Daily Scrum Inspects Progress to the Sprint Goal

Scrum Master pitch: The Daily Scrum is a planning event, not a status report to the Scrum Master.

15-minute event for Developers

Choose any useful structure

Expose impediments and adjust plan

Detailed problem-solving happens after

Workplace signal: each person reporting upward. Better move: Let Developers inspect the goal and re-plan together.

## Sprint Review Is a Working Session

Scrum Master pitch: A Sprint Review changes what the team understands and may change what it does next.

Inspect the outcome

Discuss environmental change

Engage stakeholders

Adapt the Product Backlog

Workplace signal: a one-way demo seeking applause. Better move: Invite evidence, disagreement, and backlog adaptation.

## Retrospective Turns Experience into Improvement

Scrum Master pitch: Improvement becomes real only when it enters the work system.

Inspect people, interactions, process, tools, and DoD

Identify helpful and harmful assumptions

Prioritize the most useful change

Add improvement to the next Sprint

Workplace signal: a long list of unowned ideas. Better move: Select one experiment with an owner and measure.

## Activity 04 - Facilitate Sprint Planning and a Sprint Goal

Alignment: K4, A2, A4

### Scenario

NovaTransit is improving a commuter app. The Product Backlog contains accessibility fixes, payment reliability work, journey-planning features, and marketing requests. Capacity is reduced by support duty and one unresolved vendor dependency.

### Roles

Scrum Master facilitator

Product Owner

Developers

Support representative

Observer

### Files and tool

Open activities/Activity-04-*/README.pdf for the full brief.

Open worksheet.xlsx and work from the Instructions sheet.

Open SCENARIO.pdf and CHECKLIST.pdf beside the workbook.

Use the Scrum activity tool where instructed: https://alfredang.github.io/scrum/

### Detailed playbook

1. Load the supplied Product Backlog worksheet and review the Scrum tool planning view.

2. Clarify Product Goal, capacity, Definition of Done, and dependencies.

3. Facilitate why, what, and how without assigning tasks.

4. Draft and test one outcome-oriented Sprint Goal.

5. Build a Sprint Backlog forecast and identify the first adaptation trigger.

6. Run a confidence check and capture unresolved risk.

### Facilitator and learner questions

1. Why is the Sprint valuable?

2. What evidence supports the forecast?

3. How does the Sprint Goal allow flexible scope?

4. Which dependency needs an explicit plan?

### Evidence to submit

Sprint Goal

Sprint Backlog forecast

Risk and confidence record

### Acceptance criteria

Answers why, what, and how

Uses capacity and Definition of Done

Keeps Developers responsible for the plan

Sprint Goal describes an outcome

Save the completed workbook as Activity-04-<TeamName>.xlsx. Complete every checkpoint in CHECKLIST.pdf before submitting the evidence pack.

## Activity 05 - Redesign the Daily Scrum Around Flow

Alignment: K4, A4, A7

### Scenario

The Daily Scrum at BrightBank lasts 35 minutes. Each Developer reports to the Scrum Master while others multitask. Blockers repeat, work piles up in testing, and the Sprint Goal is not mentioned.

### Roles

Scrum Master

Developers

Product Owner observer

Flow analyst

Team coach

### Files and tool

Open activities/Activity-05-*/README.pdf for the full brief.

Open worksheet.xlsx and work from the Instructions sheet.

Open SCENARIO.pdf and CHECKLIST.pdf beside the workbook.

Use the Scrum activity tool where instructed: https://alfredang.github.io/scrum/

### Detailed playbook

1. Use the Scrum tool board and mock flow data to inspect progress toward the Sprint Goal.

2. Identify work-in-progress, aging items, blockers, and dependency signals.

3. Design a 15-minute Developer-owned structure.

4. Run the event with the facilitator silent for the first five minutes.

5. Move detailed problem-solving to a follow-up huddle.

6. Compare baseline and redesigned behaviours.

### Facilitator and learner questions

1. What decision must the Daily Scrum enable?

2. Which items threaten the Sprint Goal?

3. What should happen after the 15 minutes?

4. How can the Scrum Master coach without taking over?

### Evidence to submit

Daily Scrum facilitation canvas

Flow diagnosis

Follow-up action record

### Acceptance criteria

Finishes within 15 minutes

Developers inspect the Sprint Goal

Creates an adapted plan

Separates event from problem-solving

Save the completed workbook as Activity-05-<TeamName>.xlsx. Complete every checkpoint in CHECKLIST.pdf before submitting the evidence pack.

## Activity 06 - Turn a Sprint Review into Stakeholder Collaboration

Alignment: K2, K4, A1, A5

### Scenario

An e-commerce team demos completed screens at Sprint Review, collects compliments, and ends. Customer-service data shows a rise in checkout confusion, but stakeholders see the backlog only after priorities are finalized.

### Roles

Scrum Master facilitator

Product Owner

Developers

Customer-service stakeholder

Commercial stakeholder

### Files and tool

Open activities/Activity-06-*/README.pdf for the full brief.

Open worksheet.xlsx and work from the Instructions sheet.

Open SCENARIO.pdf and CHECKLIST.pdf beside the workbook.

Use the Scrum activity tool where instructed: https://alfredang.github.io/scrum/

### Detailed playbook

1. Review the Increment evidence and customer mock data.

2. Design a working-session agenda around outcome, environment, and options.

3. Invite stakeholders to inspect evidence and surface changed assumptions.

4. Facilitate conflicting views without promising all requests.

5. Adapt Product Backlog ordering with the Product Owner accountable.

6. Capture learning and the next validation step.

### Facilitator and learner questions

1. What changed in the operating environment?

2. Which evidence should influence ordering?

3. How is a Review different from a demo?

4. What experiment reduces the largest uncertainty?

### Evidence to submit

Sprint Review agenda

Stakeholder feedback map

Adapted backlog rationale

### Acceptance criteria

Uses a real Increment and evidence

Engages stakeholders in decisions

Leaves Product Owner accountability intact

Ends with backlog adaptation or a reason not to adapt

Save the completed workbook as Activity-06-<TeamName>.xlsx. Complete every checkpoint in CHECKLIST.pdf before submitting the evidence pack.

# Topic 4 - Scrum Project Management and Evidence

Alignment: K4, K6, A2, A4, A5, A6. goals | forecasting | flow | burn charts | experimentation | change.

## Manage Outcomes Across Three Horizons

Scrum Master pitch: Goals stabilize purpose while plans remain adaptable.

Product Goal gives long-term direction

Sprint Goal focuses the current Sprint

Definition of Done protects quality

Daily plan adapts within the Sprint

Workplace signal: teams tracking tasks without outcome. Better move: Connect every forecast to a goal and evidence.

## Forecast with Evidence, Not Certainty

Scrum Master pitch: A forecast is a probability informed by history, not a promise extracted from the team.

Throughput shows completed items

Cycle time shows elapsed flow

Velocity is local planning evidence

Capacity reflects current constraints

Workplace signal: velocity used as a target across teams. Better move: Use trends for conversation, never performance ranking.

## Read Burndown and Burnup Together

Scrum Master pitch: Charts reveal patterns; the team must still interpret causes and decide.

Burndown shows remaining work

Burnup separates progress from scope change

Both require transparent definitions

Neither measures customer value

Workplace signal: a flat line blamed on individuals. Better move: Ask what changed in scope, flow, quality, or dependencies.

## Design Safe-to-Learn Experiments

Scrum Master pitch: An experiment is disciplined learning under uncertainty.

State a testable hypothesis

Limit cost and time

Define evidence before starting

Decide pivot, persevere, or stop

Workplace signal: an idea launched without success criteria. Better move: Pre-commit to the decision rule.

## Change Management Through Scrum

Scrum Master pitch: Scrum events provide repeated opportunities to involve people and adapt change.

Create awareness through transparency

Build desire through participation

Develop knowledge and ability through practice

Reinforce with cadence and evidence

Workplace signal: change communicated only at launch. Better move: Use every Sprint as a feedback and reinforcement cycle.

## Activity 07 - Interpret Burn Charts and Flow Metrics

Alignment: K4, K6, A4, A6

### Scenario

A public-services team reports stable velocity, but work regularly carries over and stakeholders are surprised by scope changes. Leaders want a dashboard to compare teams, while Developers want evidence that helps them improve.

### Roles

Scrum Master

Developers

Product Owner

Delivery leader

Data analyst

### Files and tool

Open activities/Activity-07-*/README.pdf for the full brief.

Open worksheet.xlsx and work from the Instructions sheet.

Open SCENARIO.pdf and CHECKLIST.pdf beside the workbook.

Use the Scrum activity tool where instructed: https://alfredang.github.io/scrum/

### Detailed playbook

1. Load the metrics workbook and view the built-in editable charts.

2. Compare burndown, burnup, throughput, cycle time, and aging work.

3. Separate observation from interpretation and judgement.

4. Identify scope, flow, quality, and dependency hypotheses.

5. Choose one improvement experiment and leading indicator.

6. Explain why velocity should not rank teams.

### Facilitator and learner questions

1. What does each chart reveal and conceal?

2. Which change is scope rather than delivery?

3. What additional evidence is needed before acting?

4. Which metric supports the Sprint Goal decision?

### Evidence to submit

Metric interpretation sheet

Evidence-to-decision map

Improvement experiment

### Acceptance criteria

Reads burndown and burnup correctly

Uses metrics as evidence not targets

Distinguishes observation and cause

Defines a measurable experiment

Save the completed workbook as Activity-07-<TeamName>.xlsx. Complete every checkpoint in CHECKLIST.pdf before submitting the evidence pack.

## Activity 08 - Run an Evidence-Based Retrospective

Alignment: K4, A5, A6, A7

### Scenario

A media team has repeated the same Retrospective actions for three Sprints. Participation is uneven, actions have no owners, and the team blames an external dependency without testing alternatives.

### Roles

Scrum Master facilitator

Developers

Product Owner

Dependency partner

Observer

### Files and tool

Open activities/Activity-08-*/README.pdf for the full brief.

Open worksheet.xlsx and work from the Instructions sheet.

Open SCENARIO.pdf and CHECKLIST.pdf beside the workbook.

Use the Scrum activity tool where instructed: https://alfredang.github.io/scrum/

### Detailed playbook

1. Use the Scrum tool retrospective view and supplied evidence pack.

2. Set a safety check and working agreement for candour.

3. Generate observations from facts before naming causes.

4. Cluster patterns and select the most useful problem.

5. Design one safe-to-learn experiment with owner, measure, and review date.

6. Close by checking confidence and psychological safety.

### Facilitator and learner questions

1. Which data contradicts the team's story?

2. What is within influence?

3. Which experiment is small enough to learn quickly?

4. How will the action enter the next Sprint?

### Evidence to submit

Retrospective evidence board

Improvement hypothesis

Experiment and follow-up record

### Acceptance criteria

Creates psychological safety

Uses facts before assumptions

Prioritizes one useful improvement

Makes ownership and measurement explicit

Save the completed workbook as Activity-08-<TeamName>.xlsx. Complete every checkpoint in CHECKLIST.pdf before submitting the evidence pack.

# Topic 5 - Scrum Artifacts and Information Radiators

Alignment: K7, A1, A2, A3, A6. Product Backlog | Sprint Backlog | Increment | commitments | collaboration.

## Product Backlog + Product Goal

Scrum Master pitch: Ordering expresses the next best use of the Scrum Team's capacity.

Emergent ordered list

Single source of product work

Items gain detail through refinement

Product Goal describes a future state

Workplace signal: priority labels with no trade-off. Better move: Order items explicitly using value, risk, learning, and dependency.

## Refinement Makes Work Ready for Conversation

Scrum Master pitch: Refinement improves shared understanding; it does not freeze requirements.

Break down and clarify items

Add description, order, and size

Developers estimate

Do not create a hidden approval gate

Workplace signal: a Definition of Ready blocking learning. Better move: Refine enough for a responsible forecast.

## Sprint Backlog + Sprint Goal

Scrum Master pitch: The Sprint Backlog is a plan by and for Developers.

Sprint Goal explains why

Selected items show what

Actionable plan shows how

Developers update it throughout the Sprint

Workplace signal: a board maintained by the Scrum Master. Better move: Make the plan visible where Developers adapt it.

## Increment + Definition of Done

Scrum Master pitch: Done means usable and transparent—not almost finished.

Usable step toward Product Goal

Additive to prior Increments

Verified against one quality standard

May be released before Sprint Review

Workplace signal: separate teams using incompatible quality bars. Better move: Create one shared Definition of Done for the product.

## Information Radiators Enable Collaboration

Scrum Master pitch: A visible artifact is useful only when people can act on what it reveals.

Show goals and current flow

Expose quality and impediments

Keep data near decision-makers

Protect transparency from vanity metrics

Workplace signal: dashboards viewed but not discussed. Better move: Pair every signal with an owner and decision cadence.

## Activity 09 - Order a Product Backlog with Customer Evidence

Alignment: K1, K2, K7, A1, A2, A3

### Scenario

A food-delivery platform has forty candidate items from customers, operations, fraud, accessibility, and growth teams. Every stakeholder labels their request high priority, and hidden dependencies cause rework during Sprints.

### Roles

Product Owner

Scrum Master

Developers

Customer advocate

Operations stakeholder

### Files and tool

Open activities/Activity-09-*/README.pdf for the full brief.

Open worksheet.xlsx and work from the Instructions sheet.

Open SCENARIO.pdf and CHECKLIST.pdf beside the workbook.

Use the Scrum activity tool where instructed: https://alfredang.github.io/scrum/

### Detailed playbook

1. Open the Scrum tool backlog view and supplied Product Backlog workbook.

2. Clarify Product Goal and customer/business evidence.

3. Score items for value, risk reduction, learning, size, and dependency.

4. Use MoSCoW or weighted ordering as a conversation aid, not an automatic answer.

5. Refine the top items with Developers and record assumptions.

6. Publish the ordered backlog and rationale.

### Facilitator and learner questions

1. Which evidence supports value?

2. What risk or learning should move earlier?

3. Which dependency changes the order?

4. Where must Product Owner judgement override a score?

### Evidence to submit

Ordered Product Backlog

Evidence and dependency matrix

Refinement notes

### Acceptance criteria

Connects order to Product Goal

Uses customer and business evidence

Makes dependencies visible

Product Owner makes the final ordering decision

Save the completed workbook as Activity-09-<TeamName>.xlsx. Complete every checkpoint in CHECKLIST.pdf before submitting the evidence pack.

## Activity 10 - Capstone Scrum Master Facilitation Plan

Alignment: K1-K7, A1-A7

### Scenario

Meridian Mobility is launching an accessible transport subscription in eight weeks. Its Scrum Team has unclear accountabilities, a long Daily Scrum, inconsistent Definition of Done, late stakeholder feedback, rising cycle time, and a Product Backlog driven by the loudest requester.

### Roles

Scrum Master

Product Owner

Developers

Customer stakeholder

Organisational leader

### Files and tool

Open activities/Activity-10-*/README.pdf for the full brief.

Open worksheet.xlsx and work from the Instructions sheet.

Open SCENARIO.pdf and CHECKLIST.pdf beside the workbook.

Use the Scrum activity tool where instructed: https://alfredang.github.io/scrum/

### Detailed playbook

1. Diagnose the operating landscape, customer needs, and Scrum anti-patterns.

2. Define Product Goal, accountabilities, and working agreements.

3. Order the Product Backlog and facilitate a Sprint Goal forecast.

4. Design Daily Scrum, Sprint Review, and Retrospective facilitation canvases.

5. Create Definition of Done and an impediment strategy.

6. Build a 30-day effectiveness scorecard and present the plan.

### Facilitator and learner questions

1. Which intervention creates the earliest useful feedback?

2. How does the plan preserve self-management?

3. What evidence will show improved effectiveness?

4. Which organisational impediment requires leadership action?

### Evidence to submit

Scrum system diagnosis

30-day facilitation plan

Artifact and event canvases

Effectiveness scorecard

Executive briefing

### Acceptance criteria

Covers K1-K7 and A1-A7

Aligns all three accountabilities

Connects events, artifacts, and commitments

Uses measures without ranking individuals

Includes an owned organisational impediment action

Save the completed workbook as Activity-10-<TeamName>.xlsx. Complete every checkpoint in CHECKLIST.pdf before submitting the evidence pack.

# Assessment Flow

1. Scan the TRAQOM QR code on the LMS.

2. Complete Assessment Digital Attendance.

3. Complete the Written Assessment, then the Case Study.

4. Upload completed answers to the LMS.

5. Sign the Assessment Summary Record.

Courseware and assessment portal: https://lms-tms.tertiaryinfotech.com/

# Sources

Course page: https://www.tertiarycourses.com.sg/wsq-scrum-master-fundamentals-for-high-performing-teams.html

Legacy trainer deck v5: reference/WSQ - Master Trainer Slides - Scrum Master Fundamentals for High-Performing Teams - v5.pptx

The Scrum Guide 2020: https://scrumguides.org/docs/scrumguide/v2020/2020-Scrum-Guide-US.pdf

Scrum.org - What is a Scrum Master: https://www.scrum.org/resources/what-is-a-scrum-master

Scrum Alliance - What is a Scrum Master: https://www.scrumalliance.org/what-is-a-scrum-master

Scrum.org - What Scrum Master: https://www.scrum.org/resources/what-scrum-master

Scaled Agile - What is a Scrum Master: https://scaledagile.com/blog/what-is-a-scrum-master/

Atlassian - Scrum Master: https://www.atlassian.com/agile/scrum/scrum-master

Asana - Scrum Master: https://asana.com/resources/scrum-master

Coursera - What is a Scrum Master: https://www.coursera.org/articles/what-is-a-scrum-master

TechTarget - Scrum Master: https://www.techtarget.com/whatis/definition/scrum-master

Scrum activity tool: https://alfredang.github.io/scrum/